CONSULTANCY TO DEVELOP JAMAICA’S NATIONAL STRATEGIC AND ACTION PLAN FOR THE PREVENTION AND CONTROL NON-COMMUNICABLE DISEASES (2022 – 2026)

# INTRODUCTION

Non-communicable diseases (NCDs) have emerged as the leading cause of death globally. Of 56.9 million global deaths in 2016, 40.5 million, or 71%, were due to non-communicable diseases (NCDs). The four main NCDs are cardiovascular diseases, cancers, diabetes and chronic lung diseases. The burden of these diseases is rising disproportionately among lower income countries and populations. In 2016, over three quarters of NCD deaths -- 31.5 million -- occurred in low- and middle-income countries with about 46% of deaths occurring before the age of 70 in these countries.

Cardiovascular diseases account for most NCD deaths, or 17.9 million people annually, followed by cancers (9.0 million), respiratory diseases (3.9million), and diabetes (1.6 million). These 4 groups of diseases account for over 80% of all premature NCD deaths. Tobacco use, physical inactivity, the harmful use of alcohol and unhealthy diets all increase the risk of dying from a NCD. Detection, screening and treatment of NCDs, as well as palliative care, are key components of the response to NCDs. These conditions are often associated with older age groups, but evidence shows that 15 million of all deaths attributed to NCDs occur between the ages of 30 and 69 years. Of these "premature" deaths, over 85% are estimated to occur in low- and middle-income countries. Children, adults and the elderly are all vulnerable to the risk factors contributing to NCDs. Metabolic risk factors contribute to four key metabolic changes that increase the risk of NCDs: raised blood pressure, overweight/obesity, hyperglycemia (high blood glucose levels) and hyperlipidemia (high levels of fat in the blood). In terms of attributable deaths, the leading metabolic risk factor globally is elevated blood pressure (to which 19% of global deaths are attributed), followed by overweight and obesity and raised blood glucose. NCDs threaten progress towards the 2030 Agenda for Sustainable Development, which includes a target of reducing premature deaths from NCDs by one-third by 2030.

NCD Mortality and Morbidity in Jamaica

In 2017, the top 5 causes of death in Jamaica were stroke, diabetes, ischaemic heart disease, Alzheimer’s disease and inter-personal violence. Nine of the top 10 causes of death were from NCDs. Premature mortality was due to stroke, diabetes, interpersonal violence, neonatal disorders and ischemic heart disease. Combining death and disability together, the top 5 risk factors contributing to DALYs (Disability Adjusted Life Years) were high plasma glucose, obesity, dietary risks, high blood pressure and tobacco use.

Global Response

In recognition of the global challenge from NCDs, the World Health Organization initiated a call to action in responding to NCDs with the passing of a resolution at the 53rd World Health Assembly in 2000 and the publication of a policy document on a Global Strategy for the Prevention and Control of Non-communicable Diseases. This has been followed by a number of global and regional initiatives and publications culminating with the holding of a United Nations High Level Meeting on Non-communicable Diseases in September 2011, with the leadership of the Caribbean countries and the acceptance of a political declaration calling on Heads of Government to reduce risk factors for NCDs and create health promoting environments, strengthen national policies and health systems, facilitate international cooperation, research and development, and monitoring and evaluation of NCDs.

Caribbean Response

The Caribbean epidemic of non-communicable diseases is the worst in the region of the Americas and also has the highest rates of premature mortality due to cardiovascular diseases (PAHO). In light of this high burden of NCDs, Heads of Government of the Caribbean Community (CARICOM) member countries met in Port of Spain in September 2007 and issued a declaration entitled “Uniting to Stop the Epidemic of Chronic Non-communicable Diseases”, now known as The Port of Spain Declaration. This declaration has proved instrumental and has served as a rallying cry to address the burden of NCDs and eventually led to the holding of the UN summit on NCDs.

Jamaican Response

In recognition of this global burden and threat of NCDs, the Ministry of Health & Wellness (MOHW) in Jamaica has had a focus on NCDs for several years and has implemented prevention and control programmes to combat this threat. The 2013-2018 strategic plan was built on the foundation of these programmes and policies and sought to ensure that Jamaica’s response to the NCD epidemic is robust, efficient and effective and will result in a significant reduction to the extent of the problem in the coming years.

# OVERALL OBJECTIVE OF THE CONSULTANCY

To develop Jamaica’s National Strategic and Action Plan for the Prevention and Control Non-Communicable Diseases and sub-plans for (1) Cancer Prevention and Control and (2) Injuries Prevention and Control (2022 – 2026)

- SPECIFIC OBJECTIVES OF THE CONSULTANCY

- Evaluate Jamaica’s National Strategic and Action Plan for the Prevention and Control Non-Communicable Diseases (2013-2018)

- Develop Jamaica’s National Strategic and Action Plan for the Prevention and Control Non-Communicable Diseases and sub-plans for Cancer Prevention and Control and Injuries Prevention and Control (2022 – 2026)

# SCOPE OF WORK

- METHODOLOGY

The consultant is expected to conduct a review of the relevant literature, analyze relevant data, attend meetings, conduct interviews (as needed) and make presentations to stakeholders

- SPECIFIC ACTIVITIES

Specific tasks of the consultancy are as follows:

- Develop the evaluation plan

- Conduct the evaluation of 2013-2018 strategic plan

- Prepare an evaluation report

- Conduct literature review (and key informant interviews (KIIs) as needed), review reports and review of the 2013-2018 NCD NSP and its two sub-plans for the prevention and control of cancer and childhood obesity

- Produce a report from the literature review (and KIIs) of the proposed revisions to the 2013-2018 strategic plan

- Conduct consultations with stakeholders

- Develop a draft strategic plan and two sub-plans with stakeholder input and appropriate impact indicators for evaluation purposes

- Develop plans of action for the draft plan and the two sub-plans with stakeholder input and appropriate process and outcome indicators for monitoring purposes

- Finalize the strategic plan and the two sub-plans with incorporation of stakeholder comments as applicable

- Prepare PowerPoint slide sets for the approved plan and both sub-plans

- DELIVERABLES

| Deliverable | Due Date | Budget (%) | Review Period | Payment Schedule |
| --- | --- | --- | --- | --- |
| Workplan with methodology for project execution | 2 weeks after contract signing | 10% | 5 days | 4 weeks after approval |
| Evaluation plan | 2 weeks after contract signing | N/A | 5 days | N/A |
| Evaluation report* | 10 weeks after contract signing | 25% | 5 days | 4 weeks after approval |
| Report: proposed revisions to the 2013-2018* | 12 weeks after contract signing | N/A | 5 days | N/A |
| First draft of the strategic plan with plan of action* | 24 weeks after contract signing | 25% | 10 days | 4 weeks after approval |
| First drafts of the sub-plans* | 28 weeks after contract signing | 15% | 10 days | 4 weeks after approval |
| Final draft of the strategic plan, sub-plans and PowerPoint slide set | 32 weeks after contract signing | 25% | 10 days | 4 weeks after approval |

*Deliverable requires a summary report of the final process used/documents reviewed

Approval of deliverables is based on the quality of the report as determined by the Director, Health Promotion and Protection Branch

- TIMELINE OF THE CONSULTANCY

January 2021 – October 2021

- REPORTING   RELATIONSHIP

The consultant reports directly to the Director, Non-Communicable Diseases and Injuries Prevention Unit (NCD Unit) and indirectly to the Director, Health Promotion and Protection Branch (HPPB)

- FUNDING OF THE CONSULTANCY

The Ministry of Health and Wellness will fund the consultancy

- SPECIFIC INPUTS TO BE PROVIDED BY THE MINISTRY OF HEALTH AND WELLNESS (MOHW)

The MOHW through the NCD Unit, HPPB will provide MOHW internal reference documents, convene stakeholder meetings and facilitate access to key informants; written comments on the draft plans and reports will also be provided.

- REQUIRED QUALIFICATIONS

- Master’s degree related to management, economics or policy with demonstrated health experience OR Health related master’s degree with demonstrated leadership and planning experience

- At least 5 years’ experience in each of the following:

  - facilitating strategic planning for health

  - national/Caribbean regional NCD Prevention and Control initiatives

  - monitoring and evaluation methodologies

- EVALUATION CRITERIA

  - Overall score of 75% or more to qualify

|  | Maximum Score |
| --- | --- |
| Qualifications - Master’s degree related to management, economics or policy (4) with demonstrated health experience (6) - Health related master’s degree (6) with demonstrated leadership and planning experience (4) | 10 |
| Experience Experience in facilitating strategic planning for health - Less than 5 years (1) - At least 5 years (5) Experience in national/Caribbean regional NCD Prevention and Control initiatives - Less than 5 years (1) - At least 5 years (5) Experience in monitoring and evaluation methodologies - Less than 5 years (1) - A least 5 years (5) | 15 |
| Technical Proposal Proposal and Methodology (20) Work Plan (10) | 30 |
| Financial Proposal | 20 |

- SPECIAL TERMS AND CONDITIONS

The Consultant will spend most of his/her time working with the implementing partners, Ministries, Department and Agencies, as well as other private and public partners working in the NCD response. No office space will be provided. The Consultant works at his/her own pace but must meet the established deadlines. All expenses should be stated in the budget as the total in the proposal is the final amount to be paid. All resources and documentation produced from this activity are owned by the Ministry of Health and Wellness and shall not be accessed, shared or published without the permission of the Ministry of Health and Wellness.